## Bug Report Log
BUG REPORT LOG – Automation Exercise E-Commerce Web Application
Project: AE-2026 ¦ QA Team ¦ Version 1.0 ¦ July 2026
Bug ID | TC ID | Module | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date | Fixed Date
BUG-001 | TC-036 | Support & Compatibility | Contact Us form submits successfully even with Email field empty | When the Email field is left blank on the Contact Us form, the form still submits and shows a success message instead of blocking it. | 1. Go to the Contact Us page. 2. Fill in Name, Subject, and Message. 3. Leave Email blank. 4. Click Submit. | Form should block submission and show a required-field validation message for Email. | Form submits successfully and shows the success message despite Email being empty. | Medium | High | Open | QA Engineer | 23-Jul-2026
BUG-002 | TC-020 | Shopping Cart | Cart quantity doesn't visually update until the page is refreshed | After setting a custom quantity and adding to cart, the cart page briefly shows the old quantity until manually refreshed. | 1. Open a product detail page. 2. Set quantity to 4. 3. Click Add to cart. 4. Open the Cart page. | Cart should immediately display quantity as 4. | Cart briefly shows quantity as 1 until the page is manually refreshed. | Low | Medium | In Progress | QA Engineer | 23-Jul-2026
BUG-003 | TC-012 | Search & Browsing | Search box doesn't trim leading/trailing spaces | Searching with extra spaces around a valid keyword returns zero results instead of trimming and matching normally. | 1. Go to the Products page. 2. Enter ' dress ' (with spaces) in the search box. 3. Click Search. | Search should trim whitespace and return the same results as 'dress'. | Search returns zero results for the padded query. | Low | Low | Open | QA Engineer | 23-Jul-2026

## Bug Summary Dashboard
BUG SUMMARY DASHBOARD – Automation Exercise AE-2026
QA Team ¦ July 2026 ¦ All figures as of report date
By Severity
Critical | 0
High | 1
Medium | 1
Low | 2
Total | 4
By Status
Open | 2
In Progress | 1
Fixed | 0
Total | 3
By Module
Support & Compatibility | 1
Shopping Cart | 1
Search & Browsing | 1
Total | 3
Key Metrics
Total Bugs Reported | 3
Defect Density (bugs per module) | 0.43
Bug Fix Rate | 0%
Critical Bugs Still Open | 0
Test Execution % | 97%